## Open Requirements
Req ID | Module | Section / Feature | Portal | User Role(s) | Requirement Summary | Priority | Status | Owner
GC-RX-001 | M01 | GC User Rights — Prescribing | provider | provider_gc | Disable all e-prescribing for GC role. E-prescribe tab, prescribe action, and prescription order type not visible or accessible to GC users. | High | Open | Justin Woller / Engineering
M01-POA-001 | M01 | POA / Authorized Representative Access | Admin Portal | All Roles | POA access requires: (1) written POA/legal authorization over health information AND (2) govt-issued photo ID. Financial-only POA expressly not sufficient. | High | Open
M01-POA-002 | M01 | POA / Authorized Representative Access | Admin Portal | All Roles | POA access activation requires staff review and explicit approval before POA holder can log in on behalf of patient. | High | Open
GC-ADM-001 | M01 | GC Admin Workload Management | Provider Portal | GC Administrator | GC Admin dashboard includes Workload Overview panel: active GCs, consult counts, SLA-at-risk counts, and a Preview & Route action for consult reassignment. | Medium | Open | Justin Woller
CTYPE-001 | M02 | Consult Type Label Clarity | Provider Portal | provider_md, provider_np | Refills labeled as distinct type (low-effort, <5 min, flat rate). Async Consults shown separately with variable time/rate indicator. | Medium | Open | Justin Woller
LAB-DASH-001 | M02 | Lab Req Count Badge on Provider Dashboard | Provider Portal | provider_md, provider_np | Dashboard displays lab req count badge (e.g., '54 Lab Req'). Clicking navigates to Lab Req module. | High | Open | Justin Woller
MGR-TS-001 | M02 | Manager Timesheet Approval | Manager Dashboard | provider_manager | Manager dashboard shows pending timesheet approvals: team member name, hours, period, and approve/reject action. | Medium | Open | Justin Woller
MSG-BAR-001 | M02 | Internal Messaging Notification Bar | Provider Portal | provider_md, provider_np, provider_ma, provider_rn | Notification bar appears below ribbon when unread internal messages exist. | Medium | Open | Justin Woller
PG-ALL-001 | M02 | Page Guide Button on Every Screen | All Portals | all | Page Guide button in topbar of every screen. Clicking opens contextual side panel with screen-specific workflow guidance. | High | Open | Justin Woller
PLK-001 | M02 | Patient Lookup — MRN & Consultation History | All Portals | MD, NP, RN, MA, GC, GCA, CT, admin | Replace generic name search with consultation history lookup supporting MRN, account number, patient name, DOB. Results show name, MRN, DOB, acct number, consult history summary. | High | Open | Justin Woller / Engineering
PROV-TOG-001 | M02 | Provider Online/Offline Toggle | Provider Portal | provider_md, provider_np | Toggle switch in dashboard header. Online = eligible for on-demand broadcasts. Offline = removed from eligibility. | High | Open | Justin Woller
PRV-DASH-001 | M02 | Provider Dashboard Ribbon | Provider Portal | provider_md, provider_np | Ribbon displays 4 live metric counts as the primary planning view. | High | Open | Justin Woller
RN-TAKE-001 | M02 | RN Take Button — Explicit Queue Claim | Provider Portal | provider_rn | Each unclaimed item in RN queue shows a Take button. Clicking assigns item to RN and removes from others' view. | High | Open | Justin Woller
SLA-TAB-001 | M02 | SLA Notifications Tab — Rename and Restructure | Provider Portal | provider_md, provider_np | Tab renamed to 'SLA Notifications'. Content restricted to SLA-based items only (overdue and approaching). | High | Open | Justin Woller
M03-HP-027 | M03 | Abnormal Result — Patient Consult Topic Selection | Patient Portal | patient | Scheduling flow for abnormal result consults must include patient-facing topic selection checklist. Selections surfaced to provider in chart before session. | High | Open | Kyro Beshay
REQ-OPEN-LAB-SELECT | M03 | Sensitive Result Preferences | Patient Portal | patient | Patient portal allows patients to select which lab results are included in provider discussion. Do-not-discuss results flagged visibly in provider chart. | High | Open | Justin Woller
REQ-OPEN-PWN-LEGAL | M03 | Legal / Compliance — PWN Telemedicine | Patient Portal |  | System restricts/allows telemedicine consult booking in PWN patient portal based on contractual terms. Pending Legal (Jessica Wheeler) confirmation. | High | Open | Justin Woller
REQ-OPEN-PWN-NOTIFY | M03 | Visit Notifications — PWN Portal | Patient Portal |  | PWN patient portal displays notification card/banner for each upcoming visit: time, provider name, visit type, pre-visit instructions. | Medium | Open | Justin Woller
REQ-OPEN-STATE-CONFIRM | M03 | State Mismatch Prevention | Patient Portal |  | Patient portal displays mandatory confirmation of patient's current physical state before prescriptive consult booking. Also checks pharmacy state match. | High | Open | Justin Woller
M03-COMM-001 | M03 | Communication Log | Provider Portal | Provider | Communication logging handled via Activity Timeline in chart right panel. No separate Log Communication button required. | P1 | Open | Blake Lusenhop
M03-DEMO-001 | M03 | Patient Demographics — Race/Ethnicity | Provider Portal | Provider | Patient chart demographic meta bar displays patient's race and ethnicity/Hispanic-Latino status alongside other demographic fields. | P2 | Open | Blake Lusenhop
DOC-LIB-001 | M04 | Document & Blurb Library — Admin Approval | Admin Portal | admin | Restrict document/blurb library uploads to Admin portal. Providers can browse and attach pre-approved content but cannot upload. Admin manages via dedicated library management section. | High | Open | Justin Woller / Kyla Patek
GC-STG-001 | M04 | Multi-Stage Genetic Test Workflow — Admin Config | Admin Portal | admin, provider_gc, provider_md | Multi-stage genetic test workflow configured in Admin portal Care Product wizard. Stages: GC Pre-Test Consult, Physician Authorization, Lab Processing & Result Delivery. Each stage trackable, payment per stage configurable. | High | Open | Justin Woller / Engineering
M04-QA-CHIP-001 | M04 | QA Queue Filtering — Care Product Chips | Provider Portal | QA Reviewer | QA Reviewer pending queue includes filter chips: All, Everly Care, BRCA Hereditary, Minor, POA. | P2 | Open | Kyro Beshay
M04-QA-CLOSE-001 | M04 | QA Closure Flags | Provider Portal | QA Reviewer | QA Reviewer portal includes Encounter Closure Flags section listing encounters closed with pre-closure validation override, showing override reason, bypassed field, provider, and timestamp. | P1 | Open | Kyro Beshay
M04-QA-VALID-001 | M04 | QA Pre-Closure Validation | Provider Portal | QA Reviewer | System performs pre-closure validation when encounter is closed. Failed checks displayed in validation panel with option to resolve or override with documented reason. | P1 | Open | Kyro Beshay
AI-CPR-001 | M05 | AI Care Plan Review — Async Consult in MPQ | Provider Portal | provider_md, provider_np | AI care plan review items populate MPQ with distinct type label. Provider pulls, reviews AI output, and completes. | Medium | Open | Justin Woller
BULK-AUTH-001 | M05 | Bulk Authorization UI Surfacing | Provider Portal | provider_md, provider_np | Bulk authorization interface visible in relevant order queues. Select all + authorize action available. | High | Open | Justin Woller
CFE-001 | M05 | Chart Finalization — Required Field Enforcement | Provider Portal | MD, NP, RN, MA, GC, GCA, CT | System prevents chart signing until all required fields in active documentation template are completed. Inline validation summary lists incomplete fields. | Critical | Open | Justin Woller / Engineering
GC-OD-001 | M05 | GC On-Demand Queue | Provider Portal | provider_gc | System supports GC On-Demand patient queue for care products with on-demand GC consultation enabled. Separate from scheduled GC consult queue. | Medium | Open | Justin Woller / Kyla Patek
GC-STG-002 | M05 | GC Multi-Stage Workflow — Chart Panel | Provider Portal | provider_gc | Test Workflow panel in GC chart displays all configured stages. Active stage shows checklist, gate warning if conditions unmet, payment trigger, and Advance action gated on completion. | High | Open | Justin Woller
LAB-MOD-001 | M05 | Lab Requisition Module — Bulk Approve | Provider Portal | provider_md, provider_np | Lab Req module shows all requisitions assigned to provider. Select All + Approve All button for batch processing. | High | Open | Justin Woller
PDE-001 | M05 | Patient Data Error Correction Workflow | Provider Portal | provider_gc, provider_gca | GC can flag patient data error from chart. Routes task to GCA queue with type 'Data Correction'. GCA corrects in Lab Module and marks complete. | Medium | Open | Justin Woller / Engineering
REQ-1185 | M05 | GCA Task Queue — Visibility | Provider Portal | provider_gca | GCA Task Queue visible to all provider_gca users, displaying pending, assigned, and in-progress tasks. | Must Have | Open | Product
REQ-1186 | M05 | GCA Task Queue — Take Action | Provider Portal | provider_gca | GCA can click Take on unassigned task to assign it to themselves, update status to Assigned, and remove from unassigned view. | Must Have | Open | Product
REQ-1187 | M05 | GCA Task Queue — Route Action | Provider Portal | provider_gca | Route action on every task opens modal to select destination: another GCA (showing open task count) or escalation to GC Provider Queue. | Must Have | Open | Product
REQ-1188 | M05 | GCA Task Queue — Task Types | Provider Portal | provider_gca | System supports GCA task types: Consult Prep, POA Verification, Report Review, Blurb Review, Stage Gate. | Must Have | Open | Product
REQ-1189 | M05 | GCA Task Queue — RN Inbound Routing | Provider Portal | provider_rn | RNs can route a patient task to GCA queue from RN queue. GCA entry includes patient ID, task type, routing reason, priority, and due date. | Must Have | Open | Product
REQ-1190 | M05 | GCA Task Queue — Provider Inbound Routing | Provider Portal | provider_md | Providers (MD, NP, GC) can create a GCA task from chart or routing modal, selecting task type, priority, due date, and routing reason. | Must Have | Open | Product
REQ-1191 | M05 | GCA Task Queue — Auto Stage Gate Routing | Provider Portal | provider_gca | System automatically routes GCA Stage Gate task when patient advances to a configured stage. Stage gate config managed in Admin portal. | Must Have | Open | Product
REQ-1192 | M05 | GCA Task Queue — POA Verification Gate | Provider Portal | provider_gca | POA Verification task requires GCA to confirm POA documentation before patient workflow can advance to scheduling. Completion is a hard gate for scheduling. | Must Have | Open | Product
REQ-1193 | M08 | GCA Task Queue — Notifications | Provider Portal | provider_gca | In-app notification + configurable email sent to all GCAs when new HIGH priority task is routed to unassigned GCA queue. | Must Have | Open | Product
REQ-1194 | M05 | GCA Task Queue — Completion | Provider Portal | provider_gca | Assigned GCA can mark task complete with required completion action. Completion records timestamp and GCA name in audit log. | Must Have | Open | Product
TPL-001 | M05 | Smart Template System — Structured Input | Provider Portal | MD, NP, RN, MA, GC, GCA, CT | Documentation templates built from structured components: dropdown, multi-select, positive/negative toggle, radio group, date picker, signature field, optional free-text. Replaces static Word/Google Doc templates. | High | Open | Justin Woller / Kyla Patek / Engineering
CRIT-Q-001 | M06 | Critical Lab Result Isolated Queue | Provider Portal | provider_rn | Critical lab results isolated from general RN queue. Separate section with 24-hour countdown per item. Items cannot pass 24 hours without escalation. | Critical | Open | Justin Woller
SLA-DFLT-001 | M06 | SLA Configuration Defaults by Task Type | Admin Portal | admin | Admin portal SLA config ships with defaults: Intake = 2 hours, Prior Auth = 4-6 hours, Critical Lab Result = 24 hours. All editable. | High | Open | Justin Woller
M07-COND-001 | M07 | Intake Configuration — Conditional Formatting | Admin Portal | admin | System supports admin-configured conditional formatting rules on intake responses that trigger downstream actions (RN escalation, chart field linking, QA flagging). | P1 | Open | Kyro Beshay
M07-COND-002 | M07 | Social Needs Screener — SDOH Linking | Admin Portal | admin | When a social needs screener answer is flagged 'At risk', system automatically links response to SDOH section of visit template and marks encounter for QA review. | P1 | Open | Kyro Beshay
D17-001 | M08 | Day 17 Automated Follow-Up Outreach | Admin Portal | admin | System automatically triggers outreach (email + SMS) to patients with abnormal lab results who have not scheduled a consult within 17 calendar days. Message content configurable in Notification Engine. | High | Open | Justin Woller / Notification Engine
URG-MSG-001 | M08 | Urgent Message Workflow — Route Button | Provider Portal | all | Route button in patient chart opens modal with route-to Department dropdown or route-to Specific User search. Urgent checkbox applies to either. Urgent messages display with visual elevation at destination. | High | Open | Justin Woller
OPEN-006 | M08 | IVR / Outbound Contact | All | All Roles | Current workflows use IVR and AI for initial outbound patient contacts. New platform must maintain this capability. Full operational design pending team input. | High | Open | Engineering / Care Team Ops
M08-NOTIFY-003 | M08 | Pre-Call Patient Notification | Patient Portal, SMS | Patient, Provider | When provider accepts patient from MPQ, platform sends patient a pre-call notification via SMS and portal push within 60 seconds. Lead time and message copy configurable per client. | High | Open | Engineering
PRES-005 | M09 | Scheduling & Routing — Online Status Gate | Admin Portal | Scheduler / Admin | Online status gate: auto-routing only assigns to Online users. Busy users eligible for lower-priority items per configuration. | P1 | Open | Justin Woller
PRES-008 | M09 | Scheduling & Routing — Clock-In/Out Log | Admin Portal | Admin | Status change Offline→Online logged as clock-in. Online/Busy→Offline logged as clock-out. Log captures: user ID, role, timestamp, status_from, status_to. | P2 | Open | Justin Woller
RN-SCHED-001 | M09 | RN On-Call Schedule — Individual Visibility | Provider Portal | provider_rn | RN on-call schedule view filtered to current logged-in RN only. No visibility into other RNs' schedules. | Medium | Open | Justin Woller
VWR-001 | M09 | Virtual Waiting Room — Auto Patient Call | Provider Portal | provider_md, patient | On-demand patients enter VWR instead of hold. System auto-triggers call to patient when provider accepts consult. | High | Open | Justin Woller
WARM-TX-001 | M09 | Automated Broadcast — Warm Transfer | Provider Portal | provider_md, provider_np, provider_ma | When MA initiates warm transfer, system identifies all online providers qualified for the care product and sends broadcast notification. First to click Accept is assigned. | High | Open | Justin Woller
LMI-001 | M10 | Lab Module Integration Strategy | Admin Portal | admin | System integrates with existing Lab Module as read/write integration point. Lab Module NOT migrated. New platform displays lab order data and results fetched from Lab Module via integration. | High | Open | Justin Woller / Engineering
M10-CE-001 | M10 | Care Everywhere — HIE Placeholder | Provider Portal | Provider | Patient chart includes 'Care Everywhere' section as placeholder for future HIE integration with Health Gorilla, Surescripts, CommonWell/Carequality. v1.0 shows coming-soon messaging and intended data sources. | P3 | Open | Blake Lusenhop
PRES-007 | M13 | Admin Presence Summary — Real-Time | Admin Portal | Admin | Admin dashboard surfaces real-time presence summary: Online/Busy/Offline counts by role. Updates on page refresh. | P2 | Open | Justin Woller
CT-MON-001 | M13 | Care Team Manager Dashboard — Physician Monitoring | Care Team Portal | Care Team Manager | CT manager dashboard includes Physician Monitoring section with real-time counts for: Untreated Rx Consults, Stuck Scheduled >3hrs, Rejected lab orders, Provider reassignment tasks. Counts refresh every 60 seconds. | Medium | Open | Engineering
CT-RX-001 | M05 | Care Team Queue — Untreated Rx | Care Team Portal | Care Team, Physician | When a prescription-eligible consult completes with no prescription created, platform auto-creates a CTQ task type 'Untreated Rx Consult'. Priority = HIGH, SLA clock starts at task creation. | High | Open | Engineering
M16-CHART-001 | M16 | DOH Reportable Disease Fields — Chart Integration | Provider Portal | Provider | DOH reportable disease fields embedded in documentation template in chart right panel. Required fields include Reported Disease, Lab Confirmed, Specimen Source, Date Onset, Date Reported, Pregnancy status, Symptoms, Treatment, Reason for Testing. | P1 | Open | Blake Lusenhop
M16-PORTAL-001 | M16 | State DOH Portal Access Page | Provider Portal | DOH Coordinator | State DOH Portals page in DOH dashboard: searchable/filterable card grid of all state submission portals. Each card shows state, agency name, portal URL, submission type, and conditions covered. | P1 | Open | Blake Lusenhop
M16-PORTAL-ADMIN-001 | M16 | State Portal Admin Config | Admin Portal | Admin | Admin DOH Configuration page includes State Portal Links section: add, edit, delete state-to-portal URL mappings. Fields: state, agency/portal name, URL, submission type, optional notes. | P1 | Open | Blake Lusenhop
M16-QUEUE-FILTER-001 | M16 | DOH Queue Filtering — SLA Age | Provider Portal | DOH Coordinator | DOH Report Queue filter bar includes SLA Age dropdown: All, Current (<1 day), Warning (1 day), Overdue (2+ days). | P2 | Open | Blake Lusenhop
M16-QUEUE-SORT-001 | M16 | DOH Queue Sorting | Provider Portal | DOH Coordinator | DOH Report Queue supports column sorting on Days Open and SLA Status columns with arrow indicator. | P2 | Open | Blake Lusenhop
M16-SLA-TREND-001 | M16 | DOH SLA Analytics — Trend Widget | Provider Portal | DOH Coordinator | DOH Dashboard includes SLA Compliance Trend widget: on-time submission % for current day and prior 7 days as a bar chart with green/amber/red threshold indicators (≥90%, 70-89%, <70%). | P2 | Open | Blake Lusenhop
M16-TPL-001 | M16 | State DOH Template Override | Admin Portal | Admin | Admin wizard Documentation Templates step includes State DOH Template Overrides section to map specific states to specific DOH reporting templates. | P1 | Open | Kyro Beshay

## Summary by Module
Module | Open Count | Key Themes
M01 — Roles & Responsibilities | 4 | GC prescribing restriction, POA access (2 items), GC Admin workload routing
M02 — Provider Portal | 10 | Dashboard ribbon, lab req badge, message bar, patient lookup, online toggle, consult types, manager timesheet, RN take button, SLA tab, page guides
M03 — Patient Portal | 7 | Abnormal result topic selection, sensitive result prefs, PWN legal/notify, state confirmation, comm log, demographics
M04 — Admin Portal | 6 | Document library, multi-stage genetic test config, QA queue chips, closure flags, pre-closure validation
M05 — Async / GCA | 16 | GCA Task Queue (8 reqs), chart finalization enforcement, lab bulk approve, smart templates, GC on-demand queue, patient data error workflow, untreated Rx CTQ task, GC multi-stage chart panel, AI care plan review
M06 — SLA Engine | 2 | Critical lab isolated queue w/ 24hr timer, SLA config defaults
M07 — Intake | 2 | Admin conditional formatting rules, social needs screener SDOH linking
M08 — Notification Engine | 4 | Day 17 automated outreach, urgent message routing, IVR/outbound contact design (OPEN-006), pre-call patient SMS
M09 — Scheduling | 5 | Virtual waiting room, warm transfer broadcast, RN on-call visibility, online gate for routing, clock-in/out log
M10 — Integrations | 2 | Lab Module integration strategy, Care Everywhere HIE placeholder
M13 — Reports & Dashboards | 2 | Admin real-time presence summary, CT manager physician monitoring
M16 — DOH Reporting | 7 | Chart field integration, state portal page, state portal admin config, queue filter/sort, SLA trend widget, template override
TOTAL | 69