## Project Plan
Provider Network 2.0 — Project Plan
Scope: Provider coverage, provider engagement across all care products, recruitment tool + process, NP network expansion, and full Salesforce buildout. Clinical ops tools and training → Project Boombox.
# | Task | Owner | Status | Depends On | Start Date | End Date | Progress Notes | Notes / Output
PHASE 1 — NETWORK RESTRUCTURING (In Motion) — Tier 1 / Tier 2 segmentation to optimize coverage and cost. No dependencies — executing now.
1.1 | Define Tier 1 provider requirements (LOCKED Jun 30) | Justin / Chanellor | Complete | — |  |  | LOCKED: Medicare/Medicaid enrolled across all licenses; 10–15 licenses; 70–80% in high-volume states; committed scheduled availability blocks. | Output: Tier 1 criteria doc — embed in Phase 2 contract template
1.2 | Subjective assessment: categorize all current providers into Tier 1 / Tier 2 | Chanellor | In Motion | 1.1 |  |  | Chanellor executing now. Use volume, state coverage, performance, and Medicare/Medicaid enrollment. Add ranking columns to provider spreadsheet. ¦ PWN-platform-declined providers (Harrell, Guirguis, Martinez, Ennabi Waller, Abraham, Salcedo, Sharma, Clermont) classified as Tier 2. Declined EverlyCare due to current platform technology — may be reassessed for Tier 1 or fall to Tier 3 once new platform is live. | Output: Tier 1 / Tier 2 classification list with rationale
1.3 | Identify Tier 1 NP candidate(s) from current network | Chanellor | In Motion | 1.1 |  |  | Isabelle confirmed: 20 licenses, strong candidate. NPs handle A1C, E-visits, care plans (not lab authorizations). | Output: NP Tier 1 shortlist — feed into Phase 5
1.4 | Contact Dr. Patel re: on-demand commitment | Chanellor | In Progress | 1.2 |  |  | 29–30 licenses. Evaluate for 20–30 hrs/week on-demand (10am–4/5pm). Confirm willingness before building into capacity model. | Output: Commitment confirmed or alternative identified
1.5 | Offboard Dr. Mojicar — redistribute $6K/month volume | Justin / Chanellor | In Motion | 1.2 |  |  | Declines Medicare/Medicaid enrollment — does not qualify for Tier 1. Confirm wind-down timeline. Redistribute volume to Tier 1 core group. | Output: Clean offboard; volume plan confirmed
1.6 | Network gap analysis — two distinct gap types to address | Chanellor | Not Started | 1.2 |  |  | GAP 1 — Single-provider risk states (AR, MS, NH): Only one provider covers these states — creates critical single-point-of-failure risk. Priority: recruit additional Tier 1/2 coverage. GAP 2 — Low PWN coverage redundancy (TX, CA, GA, IL, NJ): High-volume PWN states with insufficient Tier 1 licensed providers to enable reliable routing. Priority: supplement/budget Tier 1 license renewals in these states and targeted recruitment. License data hygiene: ~63 licenses expiring within 90 days (large IL batch due 7/31), 2 already expired, 6 FL licenses missing expiration dates — focus hygiene effort on Tier 1 providers only before acting. | Output: Gap map with two-tier priority list (Gap 1 risk states + Gap 2 redundancy states) — feeds Phase 3 recruitment campaign and Phase 6 coverage management
1.7 | Temporary workaround: configure Tier 1 providers as earliest option in CX scheduling (Retool) | Justin / IT | Not Started | 1.2 |  |  | APPROVED Jun 30. Hardcode Tier 1 providers as earliest available slot in CX interface until automated routing is built in new platform. Brief CX team on warm transfer process. | Output: Retool configured; CX briefed
1.8 | Financial impact analysis: existing rates vs. Tier 1/2 restructured spend | Justin / Finance | Not Started | 1.2 |  |  | Required before Ben sees numbers. Model current spend vs. new structure. Flag any >10% variance. Validate Dr. Patel on-demand cost (~$150–200K/yr) against volume break-even. | Output: Financial impact summary — leadership approval required before rate sign-off
1.9 | Coordinate with Misty — insert ops into Verily sales process | Justin | Not Started | — |  |  | Verily (Alphabet/Salesforce-backed) weight management opportunity. Confirm network capacity before sales commits. May require extended or 24/7 coverage model. | Output: Ops capacity confirmed for Verily pitch; requirements documented
SHORT TERM IMPROVEMENTS — Cross-team actions required to enable the on-demand pilot. No project plan dependencies — begin immediately.
STI.1 | Comms-journey visibility across all enterprise programs | Justin / Comms | Not Started | — |  |  | Required before on-demand pilot can launch. Need visibility into when and in which state an on-demand visit can be offered across every enterprise program. | Output: Access/visibility confirmed — on-demand pilot unblocked
STI.2 | Establish advance-notice process for ad hoc campaigns | Justin / Marketing | Not Started | — |  |  | Ad hoc campaigns drive volume spikes requiring Tier 1 staffing adjustments. A defined advance-notice process must be in place before pilot launch. | Output: Process defined; Tier 1 team briefed in advance of each campaign
STI.3 | Confirm Healthie scheduled hours cover ALL encounter types — no double-counting | Chanellor | Not Started | — |  |  | Healthie hours must cover all scheduled encounters across consumer, DxS, and enterprise — not just one program. Volume is growing fast across all three channels. Committed hours cannot be double-counted between programs. | Output: Healthie hour allocation confirmed by program with no double-counting
STI.4 | Iterable journey access — cross-train team, eliminate single point of failure | Justin / Ricardo | Not Started | — |  |  | Ricardo is currently the only person with visibility into Iterable journeys. Must cross-train at least one team member and grant direct access before pilot to eliminate single point of failure. | Output: Team cross-trained; direct Iterable access granted to backup resource
PHASE 2 — RATE & CONTRACT FOUNDATION — Establishes the pricing and legal framework for provider engagement. Phase 3 (Recruitment) and Phase 4 (Salesforce) both depend on this being done.
2.1 | Document current provider rate structure across all programs | Justin / Chanellor | Not Started | — |  |  | Catalog all existing rates, flat-rate history, known inconsistencies by program. Foundation for financial impact analysis. | Output: Rate inventory — all programs, all providers
2.2 | Consult tier durations confirmed (LOCKED Jun 25) | Justin / Chanellor | Complete | — |  |  | LOCKED: Simple <15 min ¦ Moderate 16–30 min ¦ Complex 31–44 min ¦ Extended 45–60 min. Applied to ALL consult types (scheduled, on-demand, real-time). | Output: Tier criteria doc with trigger logic — embed in contract template
2.3 | Clarify consult tier assignment logic with Rachel and Gabe | Chanellor / Rachel / Gabe | In Progress | 2.2 |  |  | Document how each care product is currently assigned a tier. Identify edge cases and gaps. Needed to configure Salesforce tier table accurately. | Output: Tier assignment logic by care product
2.4 | Define video vs. telephonic rate differential | Justin / Chanellor | Not Started | 2.2 |  |  | ~$3 difference approved in principle (Jun 18). Video higher; telephonic lower. Validate against financial model and market benchmarks. | Output: Rate table with video/telephonic split by tier
2.5 | Confirm async consultation flat rates (LOCKED Jun 18) | Justin / Chanellor | Complete | 2.2 |  |  | LOCKED: True async (1.5–2.5 messages/case) = $25 flat. Refill = $10 flat. EW360 one-off care plan sessions classified as 'educational' — not true async. | Output: Async rate definitions — embed in contract template
2.6 | Define tiered provider compensation by license count | Justin / Finance | Not Started | 2.4 |  |  | License tiers: 0–15, 15–30, 30+ licenses. Higher tier = slightly higher base rate. Ensure Tier 1 network economics are sustainable. | Output: Provider compensation matrix by tier and license count
2.7 | Lab authorization pay model — evaluate per-order vs. monthly stipend | Justin / Gabe / Finance | Not Started | — |  |  | Consult Gabe re: legal/compliance constraints on per-order incentives for lab authorizations. If cleared, coordinate with Ben/Max on per-order rate. | Output: Legal determination + rate decision
2.8 | Scheduled vs. on-demand pay parity (LOCKED in principle Jun 25) | Justin / Finance | Not Started | 1.8 |  |  | LOCKED: Equal pay for scheduled and on-demand across all tiers. Validate in financial impact analysis (1.8) before finalizing. No budget spike acceptable. | Output: Financial confirmation — rate table finalized
2.9 | Benchmark rates vs. market (MDLive, Teladoc) | Justin | Not Started | 2.4 |  |  | Validate rate competitiveness. Focus on Extended tier (~$52). Ensure DTC non-acute model aligns with market. | Output: Benchmark comparison — input to rate finalization
2.10 | Draft base contract template with tiered service addendum | Justin / Legal | Not Started | 2.6,2.7,2.8 |  |  | Base contract: standard terms. Tiered addendum: rate by license count, video/telephonic split, async flat rates, Tier 1 scheduled availability requirements, notification process for new care products. | Output: Contract template v1 — ready for legal review
2.11 | Define notification process for new care products (LOCKED Jun 25) | Justin / Legal | Not Started | 2.10 |  |  | LOCKED: New products added via email notification specifying tier assignment. No contract amendment required. Process defined in contract language. | Output: Notification template + process embedded in contract
2.12 | Define collaboration agreements process (NP oversight) | Justin / Legal | Not Started | 2.10 |  |  | Formalize NP supervision/collaboration agreement workflow. Required for NP expansion. Document process and add to Salesforce contract management module. | Output: Collaboration agreement process doc
2.13
2.14 | Financial impact analysis: current rates vs. new tier model | Justin / Finance | Not Started | 2.6,2.8 |  |  | Full comparison of current spend vs. proposed new rates across all programs, modalities, and provider types. Flag variances >10%. Required before Ben/leadership approval. | Output: Financial model with scenario analysis — present to Ben
2.15 | Rate structure sign-off with Finance and Clinical leadership (GATE) | Justin | Not Started | 2.13,2.14 |  |  | Hard dependency gate. Formal sign-off required. Unlocks contract execution and Salesforce buildout. | Output: Approved rate structure — Phase 4 Salesforce buildout unblocked
2.16 | Audit existing provider agreements | Justin / Chanellor | Not Started | 2.15 |  |  | Map all active contracts. Identify non-standard terms, custom amendments, inconsistencies. Sequence migration to new standard contract. | Output: Contract audit log with required changes per provider
2.17 | Define provider migration plan: existing contracts to new standard | Justin / Chanellor | Not Started | 2.16 |  |  | Tier 1 providers migrate first (updated contract with scheduled availability requirements). Sequencing, communication approach, opt-out handling. | Output: Migration plan with provider-by-provider sequencing
2.18 | Execute updated contracts with all active providers | Justin / Chanellor / Legal | Not Started | 2.17 |  |  | All active providers on standardized contract. Tier 1 contracts include scheduled availability requirements and Medicare/Medicaid enrollment confirmation. | Output: 100% of active providers on new standard contract
PHASE 3 — RECRUITMENT TOOL, RESOURCES & PROCESS — Can begin now. Implements the new recruitment platform, defines the process, and allocates the right resources to run expansion.
3.1 | Map current state recruitment process end-to-end | Justin / Chanellor | In Progress | — |  |  | Document intake, credentialing, and management steps. Identify manual pain points, handoff gaps, and bottlenecks. Foundation for tool requirements. | Output: Current-state process map
3.2 | Complete recruitment platform evaluation (FizzMP vs. alternatives) | Justin | In Progress | 3.1 |  |  | FizzMP leading candidate (~$3–5K/yr, Jun 25). Evaluate vs. PracticeMatch, PhysEmp, DirectShifts. Confirm: cost, 1099 MD/DO/NP sourcing quality, Salesforce integration capability. | Output: Platform scorecard with recommendation
3.3
3.4 | Define resource allocation model for network expansion | Justin | Not Started | 3.1 |  |  | Evaluate Stephanie for recruitment execution role. If unavailable, plan for 60–90 day external hire. Define role scope: managing recruitment pipeline, provider onboarding coordination, Salesforce management. | Output: Resource decision + job description if hiring needed
3.5 | Identify and confirm recruitment resource (Stephanie or external hire) | Justin / Chanellor | Not Started | 3.4 |  |  | Chanellor to gauge Stephanie's interest and capacity. If Stephanie not available, initiate external hiring process immediately given 60–90 day timeline. | Output: Resource confirmed and onboarded into recruitment role
3.6 | Design end-to-end recruitment process for provider expansion | Justin / Chanellor | Not Started | 3.2,3.3 |  |  | Define: sourcing → outreach → screening → credentialing → contract → activation. Include Tier 1 vs. Tier 2 pathways. Build SLAs for each stage. | Output: Recruitment process playbook
3.7 | Build targeted recruitment campaign for priority gap states | Chanellor / Recruitment Resource | Not Started | 1.6,3.5,3.6 |  |  | Use network gap analysis (1.6) to drive recruitment. Arkansas, Mississippi, New Hampshire priority. Expand to all 14 single-provider states. | Output: Active recruitment pipeline for gap states
3.8 | Define and launch Medicaid/Medicare expansion outreach to existing providers | Chanellor | Not Started | 2.18 |  |  | Survey existing providers on Medicare/Medicaid enrollment willingness and state license expansion capacity. Required for Tier 1 qualification. | Output: Provider survey results + action plan for enrollment gaps
PHASE 4 — SALESFORCE BUILDOUT (All Tracks) — Track A (Contracts/Rates) blocked until Phase 2 gate. Track B (Recruitment) can begin after Phase 3. Track C (NP Oversight) begins Phase 5.
4A.1 | TRACK A: Map Salesforce data model — contracts, rates, providers, coverage | Justin / IT / SF Admin | Not Started | 2.15 |  |  | Define objects: Provider, Contract, Rate Tier (by license count + modality), Care Product, Tier 1/2 Classification, Notification Log, State Coverage. | Output: Salesforce data model document
4A.2 | Build contract repository in Salesforce | IT / SF Admin | Not Started | 4A.1 |  |  | All provider contracts centralized. Linked to rate tier, license count, modality (video/telephonic/async), Tier 1/2 status, scheduled availability blocks, Medicare/Medicaid enrollment status. | Output: Contract repository live
4A.3 | Configure rate and tier tables (by license count, modality, consult tier) | IT / SF Admin | Not Started | 4A.1 |  |  | Rates auto-applied based on: provider license count tier, consult tier (Simple/Moderate/Complex/Extended), and modality (video vs. telephonic; async flat rate). Scheduled = on-demand (equal pay). | Output: Rate tables configured — billing pulls from these automatically
4A.4 | Configure product notification workflow (new product → tier assignment via email) | IT / SF Admin | Not Started | 4A.2,4A.3 |  |  | Replaces contract amendment process. Email notification to providers defines tier assignment for new care product. Creates audit trail in Salesforce. | Output: Notification workflow live
4A.5 | Configure contract renewal and license expiry alerts | IT / SF Admin | Not Started | 4A.2 |  |  | Proactive alerts to ops team for expiring agreements and license renewals. Ensures Tier 1 Medicare/Medicaid enrollment stays current. | Output: Alert rules configured
4A.6 | Build provider coverage map and dashboard in Salesforce | Justin / IT | Not Started | 4A.1 |  |  | Visual map by state showing: Tier 1 vs. Tier 2 providers, coverage gaps, pipeline counts (credentialing, onboarding, active). Replaces Lovable manual spreadsheet. | Output: Coverage dashboard live — real-time visibility
4A.7 | Configure billing reporting: payment reports from contract and rate data | IT / SF Admin | Not Started | 4A.2,4A.3 |  |  | Automated payment reports by provider, program, tier, modality, period. Finance pulls directly from Salesforce. Replaces manual invoicing. | Output: Payment reports configured — manual invoicing replaced
4A.8 | Salesforce → Snowflake integration for centralized network reporting | Justin / Data/Analytics | Not Started | 4A.2 |  |  | Connect Salesforce to Snowflake for high-level oversight, forecasting, and trend analysis by state, program, and provider tier. Feeds clinical reporting channel. | Output: Integration live — centralized dashboard replacing siloed manual reports
4A.9 | UAT: All agreement management, rate, and billing workflows | Justin / Chanellor / Finance | Not Started | 4A.2,4A.3,4A.4,4A.5,4A.6,4A.7
4B.1
4B.2 | Configure credentialing workflow in Salesforce/Verifiable | IT / SF Admin | Not Started | 3.3 |  |  | NPDB check, state license verification, malpractice, document collection, system access provisioning. Linked to Tier 1 Medicare/Medicaid enrollment requirement. | Output: Credentialing workflow automated in Salesforce
4B.3 | UAT: Recruitment and credentialing workflows | Justin / Chanellor | Not Started | 4B.1,4B.2
4C.1 | TRACK C: Configure NP state-based licensing algorithm in Salesforce | Justin / IT | Not Started | Phase 5 requirement |  |  | Algorithm automatically applies state NP practice requirements (collaborative vs. independent) and assigns oversight/supervising physician. Replaces manual tracking by Chanellor. | Output: Licensing algorithm live — compliance managed automatically
4C.2 | Configure collaboration agreement workflow in Salesforce | Justin / Chanellor / Legal | Not Started | 4C.1,2.12 |  |  | Oversight assignment, collaboration agreement execution, ongoing compliance tracking. Integrated with contract repository (4A.2). | Output: Collaboration agreement workflow automated
4C.3 | UAT: NP oversight and collaboration agreement workflows | Justin / Chanellor | Not Started | 4C.1,4C.2
PHASE 5 — NP NETWORK EXPANSION — Own phase. Can begin strategy work now; execution depends on Phase 2 contracts and Phase 4C Salesforce NP tools.
5.1 | Define NP network strategy: coverage goals and oversight requirements | Justin / Chanellor | Not Started | 1.3 |  |  | How many NPs? Which states are priorities? What oversight model (collaborative vs. independent practice by state)? Define Tier 1 NP criteria. Isabelle already identified as Tier 1. | Output: NP network strategy document
5.2 | Define NP scope of practice by state — product and consult eligibility | Chanellor / Legal | Not Started | 5.1 |  |  | NPs cannot do lab authorizations. Define which care products and consult types NPs can handle state-by-state. Feed into Salesforce licensing algorithm requirements. | Output: NP scope matrix by state — feeds 4C.1
5.3
5.4 | Develop NP-specific contract template and rate structure | Justin / Legal | Not Started | 2.13,5.2 |  |  | NP contract mirrors MD/DO base contract but scoped to NP-eligible care products. Include collaboration agreement addendum. Rates reflect NP scope vs. MD/DO rates. | Output: NP contract template — legal approved
5.5 | Identify NP coverage gaps: priority states for recruitment | Chanellor | Not Started | 1.6,5.1 |  |  | Cross-reference network gap analysis (1.6) with NP-eligible care products and states. Prioritize states where NPs can independently fill coverage without MD/DO requirement. | Output: NP recruitment priority list by state
5.6 | Launch NP recruitment campaign | Chanellor / Recruitment Resource | Not Started | 3.5,5.4,5.5 |  |  | Use selected recruitment platform and process (Phase 3). Target 1099 NPs with multi-state licenses. Focus on independent practice states for lower overhead. | Output: Active NP pipeline in Salesforce
5.7 | Onboard and credential Tier 1 NPs | Chanellor | Not Started | 5.6,4B.2 |  |  | Use Salesforce/Verifiable credentialing workflow. Confirm multi-state licenses, malpractice, NPI. Execute collaboration agreements where required. | Output: NP Tier 1 providers credentialed and contracted
5.8 | Validate NP network coverage against product and state requirements | Justin / Chanellor | Not Started | 5.7 |  |  | Confirm NP network fills targeted gap states for eligible care products. Verify collaboration agreements are in place where required. Sign off before full activation. | Output: NP network coverage validated — activate in scheduling system
PHASE 6 — FORECASTING & COVERAGE MANAGEMENT — Runs in parallel. Model is built; needs real data and integration with Salesforce.
6.1 | Confirm consult duration matrix: product × modality × visit type | Justin / Chanellor / Rachel | Not Started | 2.3 |  |  | Each care product mapped to: modality (Video/Telephonic/Async) × visit type (Initial/Follow-up/Refill/Educational) × duration. Update Product Catalog in Forecasting Model. | Output: Duration matrix populated in Provider_Network_Forecasting_Model.xlsx
6.2 | Pull real volume data by program and channel | Justin / Finance / Data | Not Started | — |  |  | Health Plan (member file sizes, conversion rates). DxS (order volume, abnormal %). DTC (kit orders, trigger rates). Replace placeholder inputs in forecast model. | Output: Forecasting model populated — all placeholders replaced with real data
6.3 | Build Tier 1 on-demand capacity model | Justin / Chanellor | Not Started | 1.4,6.2 |  |  | Model Dr. Patel (or equivalent) at 20–30 hrs/week. Calculate break-even volume at ~$150–200K annual cost. Confirm sufficient demand to justify dedicated hours before committing. | Output: On-demand capacity model + break-even analysis
6.4 | CMS GLP-1 approval — model prior auth volume impact | Justin / Chanellor | Not Started | 6.2 |  |  | CMS approved GLP-1 for Medicare/Medicaid — expected increase in prior auth demand. Quantify in forecast model. Confirm Tier 1 network can absorb without additional providers. | Output: GLP-1 volume impact assessment
6.5 | Integrate Salesforce/Snowflake data feeds into forecast model | Justin / Data | Not Started | 4A.8 |  |  | Replace manual data pulls with live Salesforce/Snowflake feeds. Forecast refreshes automatically as volume and provider data updates. | Output: Automated forecasting model with live data
6.6 | Ongoing: monthly coverage review using Salesforce dashboard | Justin / Chanellor | Not Started | 4A.6,6.5 |  |  | Monthly review of coverage map, provider tier health, volume vs. capacity, and gap state recruitment progress. Replace current manual spreadsheet reviews. | Output: Recurring monthly coverage review process established

## Decisions Log
Provider Network 2.0 — Locked Decisions
# | Decision | Detail / Rationale | Date | Owner | Impacts
1 | Platform migration date | January 11, 2027 for full network migration. | Jun 9 | Justin | All timelines work backward from this date.
2 | Salesforce as full network hub | Recruitment, contracts, rates, billing, coverage reporting all centralize in Salesforce. Full buildout in Phase 4. | Jun 9 | Justin | Phase 4 builds this out completely.
3 | Provider training incentive | $500 payout for completing all training within 7 business days. → Project Boombox. | Jun 9 | Justin / Finance | Boombox owns implementation.
4 | 20-minute consultation window | Executive decision — applies to all consult types. | Jun 9 | Leadership | Configure in scheduling system.
5 | Formal product names only | No internal nicknames across all communications and systems. | Jun 9 | Justin | Enforce in Salesforce configuration.
6 | Consult tier durations (LOCKED) | Simple <15 min ¦ Moderate 16–30 min ¦ Complex 31–44 min ¦ Extended 45–60 min. All consult types. | Jun 25 | Justin / Chanellor | Embed in contract template (2.10). Configure in Salesforce rate table (4A.3).
7 | Async flat rates (LOCKED) | True async = $25 flat (1.5–2.5 messages/case). Refill = $10 flat. EW360 one-off sessions = 'educational' — not true async. | Jun 18 | Justin / Chanellor | Embed in contract. Configure in billing (4A.7).
8 | Video vs. telephonic rate split | ~$3 differential approved in principle (video higher). Confirm in financial model (2.14). | Jun 18 | Justin / Chanellor | Rate table (2.4) → Salesforce (4A.3).
9 | Scheduled vs. on-demand pay parity | Equal pay across all tiers. Pending financial impact confirmation (1.8). | Jun 25 | Justin | Confirm in 1.8 before finalizing rate table.
10 | New care products via notification | New products added via email notification to providers — tier assignment only. No contract amendment. | Jun 25 | Justin / Legal | Notification workflow (4A.4).
11 | Tier 1 / Tier 2 network structure (LOCKED) | Tier 1: Medicare/Medicaid enrolled; 10–15 licenses; 70–80% high-volume states; committed scheduled availability. Tier 2: overflow. | Jun 30 | Justin / Chanellor | Phase 1 executing now.
12 | Temporary Retool workaround approved | Tier 1 providers hardcoded as earliest scheduling option in CX interface until platform auto-routing is built. | Jun 30 | Justin / IT | Task 1.7.
13 | Dr. Mojicar offboard | Declines Medicare/Medicaid enrollment; removed from network. $6K/month redistributed to Tier 1. | Jun 30 | Justin / Chanellor | Task 1.5.
14 | Humana audit deferred | Audit deferred until Verifiable is fully operational. | Jun 25 | Chanellor | Chanellor managing — collect NPDB credits, update policies, schedule dry run.
15 | DOH reporting automation | Automate DOH abnormal result reporting — add to new platform requirements. → Project Boombox. | Jun 18 | Chanellor / Justin | Boombox owns.
16 | DTC non-acute telehealth offering | Standard DTC non-acute service (like MDLive) to launch on new platform. → Project Boombox. | Jun 18 | Justin | Boombox owns.

## Summary
Provider Network 2.0 — Summary
KEY DATES & GATES
Migration Target | January 11, 2027
Phase 2 Rate Sign-off (Gate) | TBD — unblocks Salesforce buildout (Phase 4) and all contract execution
Verifiable Go-Live | Pending — unblocks Humana audit dry run
Phase 4 Salesforce UAT | TBD — depends on Phase 2 gate
SCOPE — WHAT'S IN PN 2.0
Network Restructuring | Tier 1/2 segmentation, coverage gaps, Dr. Patel/Mojicar, Verily
Rate & Contract Foundation | Tier durations, video/telephonic split, async rates, contract template, legal review
Recruitment Tool & Process | FizzMP evaluation, Salesforce recruitment module, resource allocation (Stephanie or hire), process design
Salesforce Buildout (All) | Contracts, rates, coverage dashboard, billing reports, Snowflake integration, NP algorithm
NP Network Expansion | Strategy, scope by state, contract template, recruitment, credentialing, coverage validation
Forecasting & Coverage Mgmt | Duration matrix, real data population, on-demand capacity model, GLP-1 impact, automated feeds
SCOPE — WHAT'S IN PROJECT BOOMBOX
Provider Onboarding & Training | Platform redesign, video modules, $500 incentive, sandbox requirements, Provider Ambassador role
Clinical Reporting & Automation | DOH reporting automation, utilization reporting, Snowflake analytics layer
Platform & Product Expansion | DTC non-acute telehealth offering, new platform requirements
CURRENT NETWORK STATE
Active Providers (Everly Care) | 8 of 11 contracted
Monthly Volume | ~1,400–1,500 consults/month
PWM Network (not yet on EW) | 40–60 providers
Network Gaps | 14 states: 1 provider ¦ 3 states: 0 providers
Dr. Mojicar | Offboarding — $6K/month to redistribute
Dr. Patel | Evaluating: 29-30 licenses, 20-30 hrs/wk on-demand
Isabelle (NP) | Tier 1 NP candidate — 20 licenses